## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (Intoduction to AI, ML and GPT) | MUST HAVE | No Dependency | Nishok A | 3- Completed
S1 | S1 | US-001 | Workflow Creation and fixing Project Deadlines | MUST HAVE | No Dependency | Nishok A | 3- Completed
S2 | S2 | US-001 | Document Discussion (Agile Template) | MUST HAVE | Excel | Nishok A | 3- Completed
S2 | S2 | US-001 | Use Case Reasearch and Preparation | SHOULD HAVE | kommunicate.io | Nishok A | 3- Completed
S3 | S3 | US-001 | Learning Python (loops, Functions, OOPs, Exception Handling) | MUST HAVE | Google Meet (Mentor) | Nishok A | 3- Completed
S4 | S4 | US-001 | Learning Natural Language Processing (Aquisation,Preprocessing,Feature Engineering,Modelling) | MUST HAVE | Google Meet (Mentor) | Nishok A | 3- Completed
S5 | S5 | US-001 | Learning Flask (Revising HTML, CSS,JS) and Structured Query Language (Sqlite) | SHOULD HAVE | Google Meet (Mentor) | Nishok A | 3- Completed
S6 | S6 | US-001 | Project Discussion Module 1 (Choosing Dataset and Preprocessing) | MUST HAVE | Kaggle | Nishok A | 3- Completed
S7 | S7 | US-001 | Project Discussion Module 2 (Model Selection and Training) | MUST HAVE | VS Code and Jupyter Notebook | Nishok A | 3- Completed
S8 | S8 | US-001 | Project Discussion Module 3 (Frontend Debelopment and Integration) | MUST HAVE | Sqlite and Flask | Nishok A | 3- Completed
S9 | S9 | US-001 | Project Discussion Module 4 (Testing and Deployment) | SHOULD HAVE | Yet to be decided | Nishok A | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 106 | 27 | 20 | 17 | 12 | 10 | 7 | 5 | 2.5 | 2 | 1 | 1 | 1 | 0.5 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project (Intoduction to AI, ML and GPT) | 2024-12-04 | 2024-12-05 | Nishok A | Others | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Workflow Creation and fixing Project Deadlines | 2024-12-06 | 2024-12-08 | Nishok A | Design | 3- Completed | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Document Discussion (Agile Template) | 2024-12-09 | 2024-12-09 | Nishok A | Others | 3- Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Use Case Reasearch and Preparation | 2024-12-10 | 2024-12-10 | Nishok A | Others | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Learning Python (loops, Functions, OOPs, Exception Handling) | 2024-12-11 | 2024-12-17 | Nishok A | Others | 3- Completed | 12 | 1 | 2 | 1 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | Learning Natural Language Processing (Aquisation,Preprocessing,Feature Engineering,Modelling) | 2024-12-18 | 2024-12-30 | Nishok A | Others | 3- Completed | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0
US-001 | TID-07 | Learning Flask (Revising HTML, CSS,JS) and Structured Query Language (Sqlite) | 2024-12-31 | 2025-01-08 | Nishok A | Others | 3- Completed | 12 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Project Discussion Module 1 (Choosing Dataset and Preprocessing) | 2025-01-09 | 2025-01-12 | Nishok A | Others | 3- Completed | 12 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Project Discussion Module 2 (Model Selection and Training) | 2025-01-13 | 2025-01-18 | Nishok A | Build | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Project Discussion Module 3 (Frontend Debelopment and Integration) | 2025-01-19 | 2025-01-25 | Nishok A | Coding | 3- Completed | 12 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-11 | Project Discussion Module 4 (Testing and Deployment) | 2025-01-26 | 2025-01-28 | Nishok A | Integration Test | 2- In Progress | 12 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Doubts in Project deadline. | Conducted a meeting where all doubts are clarified by the mentor.
Sprint 2 | Day 7 | Difficulty in identifying all potential use cases due to incomplete information. | Conducted additional research and consulted online resources to fill gaps.
Sprint 3 | Day 11 | Doubts in Polymorpism and Exception handling. | Conducted a meeting where all doubts are clarified by the mentor.
Sprint 4 | Day 27 | Doubts in Feature Engineering(TF-IDF). | Conducted a meeting where all doubts are clarified by the mentor.
Sprint 5 | Day 36 | Doubts in creating Virtual Environment. | Conducted a meeting where all doubts are clarified by the mentor.
Sprint 6 | Day 38 | Doubts in collection and useage of Datasets. | Conducted a meeting where all doubts are clarified by the mentor.
Sprint 7 | Day 44 | Doubts in selecting Models. | Conducted additonal research and tested utpo 14 models to compare their accuracy.
Sprint 8 | Day 50 | Doubts in using Route in Flask | Researched over online resources and learned efficient way to use route.
Sprint 9 | Day 55 | Presenting my Project to Mentor seeking further improvments, comments and guidence. | Conducted a meeting where comments and suggestion about my project given by mentor.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-04 | 2024-12-08 | Nishok A | Reasearch about Project and Workflow Creation | Assuming Project Requiremnts | Finalizing Project Deadlines | Sheduled a meeting with team and team mentor.
2 | Sprint 2 | 2024-12-09 | 2024-12-10 | Nishok A | Agile Documentation and Use Case research | Workflow Creation | Writing Agile Documentation | Sheduled a meeting with team and team mentor.
3 | Sprint 3 | 2024-12-11 | 2024-12-17 | Nishok A | Learning Python Concepts | Use Case research | Practicing Python | Done Assignments given by mentor on time.
4 | Sprint 4 | 2024-12-18 | 2024-12-30 | Nishok A | Learning Natural Language Processing | Learning Python Concepts | Paractice Machine Learning | Done Minor Projects assigned by mentor.
5 | Sprint 5 | 2024-12-31 | 2025-01-08 | Nishok A | Learning Flask and SQL | Learning Natural Language Processing | Practicing Sqlite | Builded a simple app in Flask with Sqlite.
6 | Sprint 6 | 2025-01-09 | 2025-01-12 | Nishok A | Aquiring Database | Learning Flask and SQL | Search for Dataset | Shearched dataset across Internet.
7 | Sprint 7 | 2025-01-13 | 2025-01-18 | Nishok A | Reasearch and Training about Models | Search for Dataset | Selecting Models | Testing and comparing accuracy of various Models.
8 | Sprint 8 | 2025-01-19 | 2025-01-25 | Nishok A | Creating Frontend and intergration | Searching Models | Intergrating frontend,Model and Databse | Done a dynamic Website for my model with Database.
9 | Sprint 9 | 2025-01-26 | 2025-01-28 | Nishok A | Testing and Deployment | Intergrating frontend,Model and Databse | Intergration testing | Done Senario testing by defining test cases.